### 2026 ACTION PLAN

Table 6.1: Annual Action Plan for 2026

| S/n | Projects | Location | Time Frame 2026 |  |  |  | Cost GH¢ |  |  |  | Project Status |  | Implementing Institution/Department |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | DACF | IGF | Others | New | Ongoing | Lead | Collab. |
|  | Objective: Reduce incidence of post-harvest loss of major staples food by 35% by the end of 2029. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Programme: Agriculture Modernization and Post Harvest Management. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.0 ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | AGRICULTURE |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Train four (4) FBOs in climate-smart agriculture | Akotekrom Aduasa Abajan Apoli Adiembra | * | * | * | * | 2,000.00 | 2,000.00 | 400.00 |  | * |  | DOA | Co-operative |
|  | Conduct Three Thousand five hundred (3,500) home and farm visits (extension delivery) | District-wide | * | * | * | * | 10,000.00 | 20,000.00 |  |  | * |  | DOA | DA |
|  | Partake in Eastern commodity Satellite Market Fair | Koforidua |  |  | * |  | 2,000.00 | 2,000.00 |  |  | * |  | DOA | DA |
|  | Vaccinate one hundred and fifty (150) dogs/cats against rabies | District-wide |  | * | * |  | 2,100.00 |  | 400.00 |  | * |  | DOA | DA |
|  | Conduct quarterly animal disease surveillance in 8 communities | District-wide | * | * | * | * | 2,100.00 |  | 400.00 |  | * |  | DOA | DA |
|  | Conduct quarterly monitoring and supervision visit of agricultural field activities in all 3 zones | District-wide | * | * | * | * | 6,600.00 |  |  |  | * |  | DOA | DA |
|  | Vaccinate 500 small ruminants against PPR in all 3 zones | District-wide |  | * | * |  | 2,100.00 |  | 400.00 |  | * |  | DOA | DA |
|  | Train 100 farmers in post-harvest management of cereals and legumes using hematic bags | District-wide |  |  | * | * | 2,500.00 |  |  |  | * |  | DOA | DA |
|  | Collect, collate and analyze agricultural data in the district | District-wide | * | * | * | * | 8,550.00 |  |  |  | * |  | DOA | DA |
|  | Provide administrative support (Insurance, roadworthiness and maintenance for 8 motorbikes and fuel for official vehicle) | Akim Swedru | * | * | * |  | 25,900.00 |  |  |  | * |  | DOA | DA |
|  | Purchase of stationeries, maintenance of office equipment | Akim Swedru | * | * | * | * | 4,200.00 |  |  |  | * |  | DOA | DA |
|  | Organize 3 fora on sustainable land management in the 3 zones. | Akim Swedru Akote Aduasa & Apoli |  |  | * | * | 3,450.00 |  |  |  | * |  | DOA | DA |
|  | Organize one (1) Research Extension Linkage Committee Meeting (RELC) | Akim Swedru |  |  | * |  | 3,000.00 |  | 500.00 |  | * |  | DOA | DA |
|  | Objective: Empower youth through entrepreneurial development programs and improved access to affordable credit by the end of 2029. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Programme: Local Economic Development |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | CO-OPERATIVE |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Sensitize twenty 20 communities on the benefits of co-operative groups | District-Wide | * | * | * | * |  | 8,100.00 | 200.00 |  | * |  | Co-operative | DA |
|  | Register twenty 20 vibrant groups | District-Wide | * | * | * | * |  | 1,800.00 | 400.00 |  | * |  | Co-operative | DA |
|  | Organize quarterly training program for all registered co-operatives on cooperative principles, good governance and group dynamics. | District-Wide | * | * | * | * |  | 1,800.00 | 400.00 |  | * |  | Co-operative | DA |
|  | Audit quarterly and inspect all registered co-operative societies in the District. | District-Wide | * | * | * | * |  | 1,800.00 | 300.00 |  | * |  | Co-operative | DA |
|  | Create at least two 2 co-operatives enterprises in the Birim South District. | District-Wide | * | * | * | * |  | 2,000.00 | 1,000.00 |  | * |  | Co-operative | DA |
|  | GHANA ENTREPRISES AGENCY |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Facilitate SMEs’ access to start-ups kits and credit | Akim Swedru | * | * | * | * | 2,000.00 | 2,000.00 | 400.00 |  | * |  | GEA | DA |
|  | WORKS |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Construct 1No. 24Hr economy market | Akim Swedru | * | * | * | * |  | 5,226,254.00 |  |  | * |  | DA | Contractor |
|  | Create 3km road access to one tourist site Pra & Birim River confluence | Apoli Beposo | * | * | * | * |  | 30,000.00 |  | 50,000.00 | * |  | DA | GTA |
|  | Complete 1no. 6-unit lockable stores | Akim Swedru | * | * | * | * |  | 694,557.36 |  | 500,000.00 |  | * | DA | Contractor |
|  | Sub-total |  |  |  |  |  | 83,100.00 | 5,992,311.36 | 4,8600.00 | 550,000.00 |  |  |  |  |

2.0 SOCIAL DEVELOPMENT

| S/n | Projects | Location | Time Frame 2026 |  |  |  | Cost GH¢ |  |  |  | Project Status |  | Implementing Institution/Department |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | DACF | IGF | Others | New | Ongoing | Lead | Collab. |
|  | Objective: To improve the quality, safety, and accessibility of basic school infrastructure by constructing, renovating, and adequately equipping 80% of under-resourced public basic schools. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Programme: Education Improvement Programme. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | EDUCATION |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Organize my First Day at School | District wide |  |  | * |  | 5,000.00 | 5,000.00 |  |  | * |  | GES | DA |
|  | Organise quarterly DEOC meetings | Swedru | * | * | * | * |  | 10,000.00 |  |  | * |  | GES | DA |
|  | Organize INSET-Math, Science & English for teachers | District wide | * | * | * | * | 8,000.00 | 4,000.00 |  |  | * |  | GES | DA |
|  | Organize quarterly community sensitization on the need to send all children to school & at the right age | District wide | * | * | * | * | 5,000.00 | 5,000.00 |  |  | * |  | GES | DA |
|  | Organize sports and Culture activities in the District | Akim Swedru | * | * | * | * | 5,000.00 | 5,000.00 |  |  | * |  | GES | DA |
|  | Organize best teacher award | District wide | * | * | * | * | 5,000.00 | 5,000.00 |  |  | * |  | GES | DA |
|  | Organize one Mock Exam for BECE Candidates (JHS 3) | District wide |  | * |  |  | 5,000.00 | 5,000.00 |  |  | * |  | GES | DA |
|  | Objective: Strengthen district health systems by enhancing service delivery, workforce capacity, and infrastructure, with a focus on equitable access to quality primary healthcare services by the end of 2029. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Programme: Education Improvement Programme. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | HEALTH |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Conduct routine Immunization/nutrition programs in all communities across the district | District-wide | * | * | * | * | 20,000.00 | 10,000.00 |  |  | * |  | DHD | DA |
|  | Organize public education and awareness campaigns on health-related issues such as TB, HIV, nutrition, NCDs, etc. | District-wide | * | * | * | * |  | 87,000.00 |  |  | * |  | DHD | DA |
|  | Intensify surveillance and response on malnutrition, NTD’s & all events of public health importance. | District-wide | * | * | * | * | 20,000.00 | 10,000.00 |  |  | * |  | DHD | DA |
|  | Train and retrain CHNs in Community Management of Acute Malnutrition (CMAM) and Infant and Young Child Feeding (IYCF)practices | District-wide | * | * | * | * | 10,000.00 | 10,000.00 |  |  | * |  | DHD | DA |
|  | Conduct food demonstrations. |  |  | * | * |  | 20,000.00 |  |  |  | * |  | DHD | SW&CD, AGRIC |
|  | Embark on public education on malaria elimination and related activities. | District-wide | * | * | * | * |  | 10,000.00 |  |  | * |  | DHD | DA |
|  | Support DHMT to conduct periodic market/ household iodized salt surveys. | District-wide |  |  | * |  | 10,000.00 |  |  |  | * |  | DHD | DA |
|  | Promote early detection & improve early case management of Neglected Tropical Diseases – NTDs. | District-wide | * | * | * | * | 12,000.00 |  |  |  | * |  | DHD | DA |
|  | Intensify campaign against teenage pregnancy in in the district. | District-wide | * | * | * | * | 25,000.000 |  |  |  | * |  | DHD | GES, DA |
|  | Embark on a regular education campaign on family planning, its methods, benefits as well as side effects. | District-wide | * | * | * | * | 12,000.00 |  |  |  | * |  | DHD | DA |
|  | Train 15 Midwives on safe motherhood. | District-wide | * | * | * | * | 7,000.00 |  |  |  | * |  | DHD | DA |
|  | Promote a well-motivated human resource for quality health care delivery through the administration of appropriate reward/motivation and incentive package for hard working staff especially those in deprived areas | District-wide | * | * | * | * | 40,000.00 |  |  |  | * |  | DHD | DA |
|  | Conduct health system research | District wide | * | * | * | * | 20,000.00 |  |  |  | * |  | DHD | DA |
|  | BIRTH & DEATH REGISTRY |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Register births and deaths | District wide | * | * | * | * |  | 1,000.00 |  |  |  | * | BDR | DHD Env’tal Health |
|  | Education and Community Sensitization on the importance of birth and death registration | Akim Awisa, Akim Beposo, Adenkrom | * | * | * | * |  | 1,000.00 |  |  |  | * | BDR | Information Department |
|  | Issuance of burial permit | Akim Swedru, | * | * | * | * |  | 2,000.00 |  |  |  | * | BDR | Env’tal Health |
|  | Organize Mobile Registration Exercise for Communities | District Wide | * | * | * | * |  | 1,000.00 |  |  |  | * | BDR | Assembly Members |
|  | Objective: Ensure equitable and sustainable access to safe, potable, and affordable drinking water for all communities within the district by the end of 2027 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Programme: Water, Environmental Health and Sanitation Programme. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ENVIRONMENTAL HEALTH |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Arrest and impound stray animals | District Wide | * | * | * | * |  |  | 5,000.00 |  | * |  | DEHU | DA |
|  | Organize annual Medical screening for food vendors | District Wide |  |  |  | * |  |  | 2,000.00 |  | * |  | DEHU | DA |
|  | Procure sanitary tools and Disinfectants | District Wide | * | * | * | * |  | 10,000.00 |  |  | * |  | DEHU | DA |
|  | Conduct quarterly School health inspections | District wide | * | * | * | * |  | 7,000.00 |  |  | * |  | DEHU | DA |
|  | Organize quarterly Public Education on Hygiene | District Wide | * | * | * | * |  | 15,000.00 |  |  | * |  | DEHU | DA |
|  | Sanitation improvement package | District Wide | * | * | * | * |  | 1,127,020.69 |  |  | * |  | DEHU | DA |
|  | Fumigate densely populated areas quarterly | District Wide | * | * | * | * |  | 487,609.90 |  |  | * |  | DEHU | DA |
|  | Organize monthly sanitation day | Akim Swedru | * | * | * | * |  | 277,871.01 | 12,000.00 |  | * |  | DEHU | DA |
|  | Solicit support and partnership to encourage construction household latrines to reduce open defecation | Selected communities | * | * | * | * |  | 198,000.00 |  | 0.00 | * |  | DEHU | DA |
|  | Objective: Strengthen capacity and leadership skills of women. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Programme: Vulnerability, Social and Child Protection Programme. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | SOCIAL WELFARE |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Conduct quarterly monitoring and registration as well as renewal of certificate of at least five (5) NGO’s | District wide | * | * | * | * | 2,000.00 | 1,000.00 | 500.00 |  |  | * | SW&CD | DA |
|  | Register at least fifty (50) Persons with Disability and other vulnerable groups | District wide | * | * | * | * | 2,000.00 | 500.00 | 500.00 |  |  | * | SW&CD | GFD DA |
|  | Provide support to persons with disability and other vulnerable groups | District wide | * | * | * | * | 2,000.00 | 4,000.00 |  |  |  | * | SW&CD | DA |
|  | Monitor the utilization of DACF to PWDs | District wide | * | * | * | * | 2,000.00 | 1,000.00 |  |  |  | * | SW&CD | GFD |
|  | Monitor the implementation of the LEAP programme | District wide | * | * | * | * | 2,000.00 |  |  |  |  | * | SW&CD | DA |
|  | Render support to ten (10) children in conflict with the law | Akim Swedru | * | * | * | * | 2,000.00 |  |  |  |  | * | SW&CD | DA |
|  | Facilitate the settling of Child maintenance, child custody, paternity and family welfare cases | Akim Swedru | * | * | * | * | 2,000.00 | 5,000.00 | 500.00 |  |  | * | SW&CD | DA |
|  | Conduct quarterly monitoring of early childhood development centre | All ECDCs | * | * | * | * | 2,000.00 | 5,000.00 |  |  |  | * | SW&CD | DA |
|  | Embark on sensitization and awareness creation of child labour in four (4) communities | Apoli Achiasehene akrua Laterfoum Apaaso | * |  |  |  |  | 5,000.00 |  |  | * |  | SW&CD | DA |
|  | Resolve successfully all reported & referral cases of child right abuses | District wide |  | * |  |  |  | 5,000.00 |  |  | * |  | SW&CD | DA |
|  | Conduct quarterly education campaign on Gender Base Violence & child rights, promotion & protection | District wide | * | * | * | * | 2,000.00 | 20,000.00 |  |  | * |  | SW&CD | DA |
|  | Engage with local authorities & decision makers to promote policies, practices that protect children | District wide |  |  |  | * |  | 4,000.00 |  |  | * |  | SW&CD | DA |
|  | Facilitate the settling of domestic violence cases | District wide | * | * | * | * | 2,000.00 |  |  |  |  | * | SW&CD | DA |
|  | Create, train and monitor 10 economic groups | District wide | * | * | * | * | 2,000.00 | 500.00 |  |  |  | * | SW&CD | DA |
|  | Train fifty (50) women on balanced diet and education on food preservation | District wide | * | * | * | * | 2,000.00 |  |  |  |  | * | SW&CD | DA |
|  | Engage at least 20 youth in Apprenticeship programme | District wide | * | * | * | * | 2,000.00 |  |  |  |  | * | SW&CD | DA |
|  | Advocate for the involvement of fifty (50) women in decision making through community sensitization | District wide | * | * | * | * | 2,000.00 |  |  |  |  | * | SW&CD | DA |
|  | WORKS DEPT. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Procure 1,220 furniture for all levels, 194 teachers’ furniture & 300 cupboards for public schools | District wide | * | * | * | * |  | 2,090,501.60 |  |  |  | * | DA | GES |
|  | Complete 1No. 2-unit KG block with furniture/ancillary facility and toilet | Atutunmirem | * | * | * | * |  | 700,000.00 |  |  |  | * | DA | GES |
|  | Complete 1No. 3-unit classroom block with furniture, 1no. Mechanize borehole & 6-seater W/C toilet | Adinkrom | * | * | * | * |  | 1,036,393.40 |  |  |  | * | DA | GES |
|  | Construct 1No. 2-unit KG block with furniture and ancillary facility | Ofosukrom | * | * | * | * |  | 1,600,000.00 |  |  | * |  | DA | GES |
|  | Construct 1No. 6-unit classroom block with furniture, 1no. Mechanize borehole & 6-seater W/C toilet | Abadjan | * | * | * | * |  | 1,036,393.40 |  |  | * |  | DA | GES |
|  | Complete 1No. 11-unit model school | Apaaso | * | * | * | * |  | 1,500,000.00 |  |  |  | * | MOE | DA |
|  | Complete 2No. 12-unit classroom block at AKISS | AKISS | * | * | * | * |  | 3,567,460.00 |  |  |  | * | MOE | DA |
|  | Complete 1no. boys dormitory block | AKISS | * | * | * | * |  | 1,000,000.00 |  |  |  | * | MOE | DA |
|  | Construct 3No. CHPS compound with furniture/equipment. | Akim Swedru Zongo Mensahkrom Asawase | * | * | * | * |  | 2,958,698.30 |  | 1,000,000.00 | * |  | DA | DHD |
|  | Complete renovation of 3No. CHPS Compounds | Apoli Ningo Akortekrom |  |  | * | * |  | 1,000,000.00 |  | 180,000.00 | * |  | DA | DHD |
|  | Facilitate the completion of 1No. District Hospital. | Akim Swedru | * | * | * | * |  | 1,500,000.00 | 3,000.00 |  |  | * | GIIF | DA |
|  | Construct 1No. Youth Dev’t Center | Akim Swedru |  |  | * | * |  |  |  | 1,089,093.00 | * |  | DA | DEHO |
|  | Construct 1No. Slaughterhouse | Akim Swedru |  |  | * | * |  |  |  | 570,000.00 | * |  | DA | DEHO |
|  | Drill and mechanized 14No. boreholes | Selected communities | * | * | * | * |  | 1,785,884.00 |  |  | * |  | DA | Contractor |
|  | Repair and maintenance of 20No. Boreholes |  | * | * | * | * |  | 304,617.60 |  |  | * |  | DA | Contractor |
|  | Sub-total |  |  |  |  |  | 257,000.00 | 22,404,449.90 | 24,000.00 | 2,839,093.00 |  |  |  |  |

3.0 ENVIRONMENT AND HUMAN SETTLEMENT DEVELOPMENT

| S/n | Projects | Location | Time Frame 2026 |  |  |  | Cost GH¢ |  |  |  | Project Status |  | Implementing Institution/Department |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | DACF | IGF | Others | New | Ongoing | Lead | Collab. |
|  | Objective: Enhance the availability, connectivity, and durability of road networks within the district by constructing, upgrading, and maintaining at least 80% of key feeder roads by the end of 2029. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Programme: Transport Infrastructure and Safety Management Programme. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | WORKS |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Prepare and implement Operation & Maintenance (O&M) Plan | Akim Swedru | * | * | * | * |  | 2,000.00 |  |  | * |  | DWD | DA |
|  | Maintain streetlights/install new ones | District-wide | * | * | * | * | 40,000.00 | 20,000.00 |  |  | * |  | DWD | DA |
|  | Prepare Health and safety reports on projects | District-wide | * | * | * | * | 2,000.00 | 5,000.00 |  |  | * |  | DWD | DA |
|  | Reshape selected roads | District wide | * | * | * | * | 3,960,000.00 |  |  |  | * |  | DA | DWD |
|  | Construct 1No. 150m footbridge | Akim Swedru |  |  | * | * |  |  |  | 589,581.00 | * |  | DA | DWD |
|  | Facilitate better telecommunication network in weak signal areas | Abadjan Akortekrom | * | * | * | * | 10,000.00 | 3,000.00 |  |  | * |  | DWD |  |
|  | Facilitate completion of 30km road | Akim Swedru – Apoli Ningo | * | * | * | * |  | 10,000.00 | 3,000.00 |  |  | * | GHA | DWD |
|  | Objective: Complete street naming and property addressing system for 3 major communities by 2027 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Programme: Spatial Development Programme. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | PHYSICAL PLANNING |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Conduct quarterly street naming and property addressing system | Swedru, Awisa and Aduasa | * | * | * | * | 10,000.00 | 200,000.00 |  |  | * |  | PPD | DA |
|  | Organize weekly Routine Building Inspection | District wide | * | * | * | * | 10,000.00 | 13,935.55 | 1,200.00 |  | * |  | PPD | Building Inspectorate Unit |
|  | Organize monthly Spatial/Technical Sub-committee meetings | Akim Swedru | * | * | * | * | 32,000.00 |  |  |  |  | * | PPD | DA |
|  | Prepare 3 zoning scheme | Swedru, Awisa and Aduasa | * | * | * | * | 10,000.00 | 24,550.00 |  |  | * |  | PPD | DA |
|  | Prepare 1 structure plan for the district | District wide | * | * | * | * | 20,000.00 | 400,000.00 |  |  | * |  | PPD | DA |
|  | Create a database for office information | Akim Swedru | * | * | * | * |  |  | 2,500.00 |  | * |  | PPD | DA |
|  | Objective: To reduce high deforestation by 40% by the end of 2028. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Programme: Climate Change and Environmental Sustainability Programme. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | FORESTRY |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Arrest and prosecution of illegal operators and wood dealers | District-Wide | * | * | * | * | 5,400.00 |  |  |  |  | * | FC | DA, GPS |
|  | Afforest 40 hectares of degraded forest | District-Wide | * | * | * | * | 34,000.00 |  |  |  |  | * | FC | DA |
|  | Engagement of Forest fringe communities to plant food crops alongside tree seedlings to augment their income and boost reforestation. | Apoli, Ningo, Ayensukrom, Kroboase, Akortekrom, Yawseiwuro Aduasa & Adenkyensu | * | * | * | * | 5,400.00 |  |  |  |  | * | FC | DA |
|  | Education/ Sensitization of fringe communities on forest conservation | District-Wide | * | * | * | * | 5,400.00 |  |  |  | * |  | FC | DA |
|  | Conduct daily inspections in the forest reserves to prevent encroachment and illegal lumbering | District-Wide | * | * | * | * | 5,400.00 |  |  |  |  | * | FC | DA |
|  | Celebrate Annual World Tree Planting Day | District-Wide |  | * |  |  | 5,000.00 | 10,000.00 |  |  |  | * | FC | DA |
|  | NADMO |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Conduct 4 durbars to sensitize 4 communities on the effects of climate change and practices that lead to climate change. | District wide | * | * | * | * | 10,000.00 | 30,000.00 |  |  | * |  | NADMO | DA |
|  | Embark on 5 zonal visits to flood-prone areas | District wide |  | * |  |  | 1,400.00 | 5,000.00 |  |  | * |  | NADMO | DA |
|  | Conduct 4 visits to public schools to educate them on early warnings of a flood, epidemics, rain, windstorm, domestic and bush fires | District wide | * | * | * | * | 2,000.00 | 5,000.00 | 1,000.00 |  | * |  | NADMO | DA, GES |
|  | Form & train 4 to 6 Disaster Volunteer Groups (DVGs) by the year 2029 | District wide | * | * |  |  | 10,000.00 |  |  |  |  | * | NADMO | DA |
|  | Embark on quarterly Radio discussions to create awareness on hazards, natural disasters & early warning signals. | Akim Swedru | * | * | * | * | 500.00 |  |  |  | * |  | NADMO | DA GNFS GHS FC |
|  | Conduct 10 visit to public schools to educate them on early warnings of flood, epidemics, rain, windstorm, domestic and bush fires | District-Wide | * | * | * | * | 1,000.00 | 25,000.00 | 1,000.00 |  | * |  | Nadmo | NCCE |
|  | Sub-total |  |  |  |  |  | 4,179,500.00 | 753,485.55 | 8,700.00 | 589,581.00 |  |  |  |  |

4.0 GOVERNANCE AND INSTITUTIONAL DEVELOPMENT

| S/n | Projects | Location | Time Frame 2026 |  |  |  | Cost GH¢ |  |  |  | Project Status |  | Implementing Institution/Department |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | DACF | IGF | Others | New | Ongoing | Lead | Collab. |
|  | Objective: Promote peaceful resolution and prevent escalation of chieftaincy disputes. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Programme: Governance, Accountability and Public Safety Improvement Programme. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | CENTRAL ADMINISTRATION |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Provide material support for community-initiated projects | District-wide | * | * | * | * |  | 250,000.00 |  |  | * |  | DA | MP |
|  | Organize quarterly and mandatory meetings of the Assembly Such as General Assembly, Sub-Committee, Executive Committee, PRCC, DISEC Management and Staff Meetings | Akim Swedru | * | * | * | * |  | 20,000.00 | 150,000.00 |  | * |  | DA | PM DAC DISEC |
|  | Operate and Maintain Official vehicles and immovable Assets annually | District wide | * | * | * | * |  | 200,000.00 |  |  | * |  | DA | DWD |
|  | Support Police Patrol throughout the district | District wide | * | * | * | * |  | 120,000.00 |  |  | * |  | DA | GPS |
|  | Collaborate with Security Forces and Traditional Authorities to resolve Chieftaincy Disputes | Akim Swedru | * | * | * | * |  | 25,000.00 |  |  |  | * | DA | GNFS GPS GAF GIS |
|  | Organize community durbar to Educate Community Members on Assembly’s Programmes and Policies | District Wide | * | * | * | * |  | 10,000.00 |  |  | * |  | DA | NCCE, ISD Community members |
|  | Pay quarterly NALAG dues | Akim Swedru | * | * | * | * |  | 55,564.59 |  |  | * |  | DA |  |
|  | Organize Independence Day anniversary celebration. | District wide | * |  |  |  |  | 60,000.00 |  |  | * |  | DA | Depts of Assembly |
|  | Organize the annual Farmers Day celebration | District wide |  |  |  | * |  | 60,000.00 |  |  | * |  | DA | DOA |
|  | PROCUREMENT UNIT |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Procure office fittings, equipment and stationaries | Akim Swedru | * | * | * | * |  | 200,000.00 |  |  | * |  | DA | Procurement Unit |
|  | Conduct quarterly Entity Tender Committee Meetings to update annual procurement plan | Akim Swedru | * | * | * | * |  | 5,000.00 |  |  | * |  | DA | Procurement Unit |
|  | Prepare Annual Procurement Plan | Akim Swedru | * | * | * | * |  | 10,000.00 |  |  | * |  | Procurement Unit | ETC |
|  | HUMAN RESOURCE MGT |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Conduct quarterly capacity building for staff including area council members | Akim Swedru | * | * | * | * |  | 100,000.00 |  |  | * |  | HR Dept | Assembly staff Assembly members |
|  | Validate Staff salary monthly | Akim Swedru | * | * | * | * |  |  | 500.00 |  | * |  | DA | HR Dept |
|  | Prepare and submit monthly Staff List | Akim Swedru | * | * | * | * |  |  | 500.00 |  | * |  | DA | HR Dept |
|  | FINANCE |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Conduct property revaluation | District-Wide | * | * | * | * |  | 500,000.00 |  |  | * |  | DA | Finance Dept., AM, PM. |
|  | Prepare Monthly, Quarterly & Annual Financial Statement | Akim Swedru | * | * | * | * |  |  | 11,600.00 | 10,000.00 |  | * | DA | Finance Dept. |
|  | MIS |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Maintain Assembly’s computers and website | Akim Swedru | * | * | * | * |  | 16,000.00 |  |  | * |  | DA | MIS unit |
|  | STATISTICS |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Conduct surveys on policies and programmes | District wide | * | * | * | * | 36,000.00 | 7,000.00 | 2,000.00 |  |  | * | Statistics | DA |
|  | INFORMATION SERVICES DEPARTMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Compile RTI manual | Akim Swedru | * | * | * | * | 2,500.00 | 1,000.00 | 500.00 |  | * |  | ISD | Assembly |
|  | Create awareness on RTI Law, central government’s policies as well as composite budget of the Assembly. | District-wide | * | * | * | * | 3,000.00 | 1,000.00 | 500.00 |  | * |  | ISD | Assembly |
|  | Objective: Develop and Implement an Area Council Infrastructure Development Plan by the end of 2027. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Programme: Sub structures improvement programme. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Facilitate at least three Area Council Meetings | Akim Swedru Aduasa | * | * | * | * |  | 8,000.00 |  |  | * |  | DA | Area Council Members |
|  | Support to two Area councils |  | * | * | * | * |  | 20,000.00 |  |  | * |  | Area Council | DA |
|  | Objective: Implement at least 85% of activities in the Medium-Term Development Plan by the end of 2029. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Programme: Co-ordination, Monitoring, Evaluation and Learning Programme. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | PLANNING & BUDGETING |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Organize quarterly DPCU and Budget Committee meetings | Akim Swedru | * | * | * | * |  | 20,000.00 | 42,000.00 |  | * |  | DA | DPCU Budget Committee |
|  | Prepare 2027 Annual Action Plan and Composite Budget | Akim Swedru |  |  | * | * |  | 50,000.00 |  |  | * |  | DA | DPCU |
|  | Organize Two Town Hall meetings to discuss the Plan and Budget Implementation | Akim Swedru | * |  | * |  |  | 30,000.00 |  |  | * |  | DA | DPCU |
|  | Organize Quarterly Monitoring and Evaluation of Development Projects | District-Wide | * | * | * | * |  | 60,000.00 |  |  | * |  | DA | DPCU |
|  | Collect and analyse socio-economic data to update District Profile | District-Wide | * | * | * | * |  | 18,000.00 |  |  | * |  | DA | DPCU |
|  | Organize Mid-Year Review Meetings for 2026 Annual Action Plan (AAP) & Composite Budget | Akim Swedru |  | * |  |  |  | 20,000.00 |  |  | * |  | DA | DPCU Budget Committee |
|  | WORKS DEPT. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Complete DCD bungalow | Akim Swedru | * | * | * | * |  | 1,041,836.04 |  |  |  | * | DA | DHD |
|  | Complete 1No. 5-bedroom DCE bungalow | Akim Swedru | * | * | * | * |  | 868,196.70 |  |  |  | * | DA | Contractor |
|  | Construct 2No. durbar ground | Aduasa Awisa |  |  | * | * |  | 500,000.00 |  |  | * |  | DA | MP |
|  | Sub-total |  |  |  |  |  | 41,500.00 | 3,802,515.35 | 206,100.00 | 210,000.00 |  |  |  |  |
|  | Grand total |  |  |  |  |  | 4,561,100.00 | 33,426,844.14 | 245,100.00 | 3,988,674.00 |  |  |  |  |